## Daily report
Index | Issue_Date | Department | Request_User | Issue_Details | Issue_Type | DRI | Solution | Status | Last_Update_Date | Not Finished Day | Finished_Date | Remark
1 | 2024-11-12 | PMC | Bell | Request to purchase printer. | Purchase | Mong | Procurement according to the process. | Done | 2024-12-03 | 21 Days | 2024-12-03 | 11/12 : Find a quote 11/14 : Wait MR.Ashton 11/15: Wait IT HQ 11/19 : Waiting for GM approval. 11/22: Wait fin Payment 2024/11/27 11/28: Waiting to pick up the item tomorrow afternoon 2024/11/28 11/29 : Waiting Setup 12/02 : Waiting for the delivery note
2 | 2024-11-28 | QC | LIANG ZUO | Register to apply for use Email for 5 employees | EMAIL | Mong | according to the process. | Done | 2024-12-04 | 6 Days | 2024-12-04 | 11/28: Wait IT HQ 12/03: Tomorrow Install for User
3 | 2024-11-03 | ADM | BOW | Laptop has a black screen and cannot be turned on. | EQ | Mong | Due to Windows updates causing Adobe updates to not work properly. Disable Adobe Updates and you can use it normally. | Done | 2024-12-03 | 30 Days | 2024-12-03
4 | 2024-11-03 | FIN | UN | Adobe pdf after printing the program does not respond. | EQ | Mong | Main printer Updating to make Unable to print from client device Wait for the main printer to finish updating. Can be used normally | Done | 2024-12-03 | 30 Days | 2024-12-03
5 | 2024-11-28 | IT | IT | Provide a quotation Monitor for Laptop | Purchase | Mong | Submit approved documents according to the steps | WIP | 2024-12-11 | 13 Days |  | 11/29 : Wait QT 12/02 : Wait HQ 12/06: Waiting for payment 12/12: Waiting to pick up the item from the seller tomorrow. 12/13: Waiting to create equipment delivery documents
6 | 2024-12-04 | CMO | MS.Ling | Ms. Aiko wants to use ERP from outside the company | IT | Mong | Install AnyDesk for remote use in | Done | 2024-12-04 | 0 Days | 2024-12-04
7 | 2024-12-04 | PMC | LanLan | There are messages that cannot be downloaded in the Mailbox. | EMAIL | Mong | Delete emails that cannot be downloaded on the webmail | Done | 2024-12-04 | 0 Days | 2024-12-04
8 | 2024-11-18 | DCC | Doris | Request to purchase PC. | Purchase | Mong | Procurement according to the process. | Done | 2024-12-04 | 16 Days | 2024-12-04 | 11/18: Wait IT HQ 11/19 : Waiting for GM approval. 11/22: Wait fin Payment 2024/11/27 11/28: Waiting to pick up the item tomorrow afternoon 2024/11/28 11/29 : Waiting Setup
9 | 2024-12-02 | PMC | BIEW | Computer memory is full | EQ | Mong | Check which part is full. Delete WeChat data from the device. | Done | 2024-12-02 | 0 Days | 2024-12-02
10 | 2024-12-09 | PUR | NUI | An employee from China came and asked to provide them with a laptop. | EQ | Mong | Prepare and test usage | Done | 2024-12-09 | 0 Days | 2024-12-09
11 | 2024-11-18 | IT | IT | Pay for EPMS Server room project | Purchase | Mong | Procurement according to the process. | Done | 2024-12-11 | 23 Days | 2024-12-11 | 11/27: Wait HQ 12/02 : Wait Paymant
12 | 2024-12-02 | PUR | Nui | 刪除採購變更單 | ERP | Ashton | Delete data which mark as 【作廢】 in DB directly | Done | 2024-12-02 | 0 Days | 2024-12-02
13 | 2024-12-02 | PMC | Oh | Email outlook data file full limit 50 GB | IT | Than | Add new data file and Archive email to local pc | Done | 2024-12-02 | 0 Days | 2024-12-02
14 | 2024-12-02 | PMC | Lan Lan | User requests mobile Wi-Fi registration | IT | Than | Register mac address and allow access to internet | Done | 2024-12-02 | 0 Days | 2024-12-02
15 | 2024-12-03 | PMC | Lan Lan | 單頭刷新 | ERP | Ashton | Update New WO into DB | Done | 2024-12-03 | 0 Days | 2024-12-03
16 | 2024-12-05 | FIN | An An | The PwC team cannot connect to the internet Enrich company. | IT | Than | Register the MAC address and reconnect to Wi-Fi | Done | 2024-12-05 | 0 Days | 2024-12-05
17 | 2024-12-05 | IT | IT | Payment Voucher for Photo Collection Software of the QC Department. | IT | Than | Payment Process | Done | 2024-12-11 | 6 Days | 2024-12-11 | 12/05: Waiting for HQ to review. 12/06: Waiting for payment
18 | 2024-12-05 | PMC | Bew | The Excel program does not respond and closes automatically during operation. | IT | Than | Update firmware, program, and Windows. | Done | 2024-12-05 | 0 Days | 2024-12-05
19 | 2024-12-05 | PUR | Nui | The computer shows a PIN code prompt during the document printing process. | IT | Than | The issue was caused by the printer settings on the computer. The problem has been resolved. | Done | 2024-12-05 | 0 Days | 2024-12-05
20 | 2024-12-06 | ADM | Bow | Prepare a document estimating the price of a label printer. | EQ | Than | Price estimate | Done | 2024-12-06 | 0 Days | 2024-12-06
21 | 2024-12-06 | PUR | Nong | Update price for old PO which it still didn't transfer to AP | ERP | Ashton | Update New WO into DB | Done | 2024-12-06 | 0 Days | 2024-12-06
22 | 2024-12-09 | PUR | Nui | 申請採購未交明細查詢清單 | ERP | Ashton | 利用之前已建立好的SQL查詢 | Done | 2024-12-09 | 0 Days | 2024-12-09
23 | 2024-12-09 | PMC | Keng | 目前工单428单头已满，请协助开新的单头 | ERP | 小汪 | 已切换到426 | Done | 2024-12-09 | 0 Days | 2024-12-09
24 | 2024-12-10 | Pur | Nuii | Request: Set up email and printer on the notebook for the purchasing department staff coming from China. | EQ | Mong | Set up and test the functionality for the user. | Done | 2024-12-10 | 0 Days | 2024-12-10
25 | 2024-12-10 | MFG | HUIHUI | The jdPrint program on the computer of the wood factory department is not functioning. | EQ | Mong | Uninstall the program and reinstall it. | Done | 2024-12-10 | 0 Days | 2024-12-10
26 | 2024-12-10 | DCC | Doris | The computer cannot switch to Chinese language. | EQ | Mong | Update Windows and fix the language settings. | Done | 2024-12-10 | 0 Days | 2024-12-10
27 | 2024-12-10 | PMC | BIEW | The email is full and cannot send or receive emails. | EQ | Mong | Delete some emails from the webmail. | Done | 2024-12-10 | 0 Days | 2024-12-10
28 | 2024-12-11 | PUR | NUII | Install meeting programs for the purchasing department. | EQ | Mong | Install tencent meeting program for User | Done | 2024-12-11
29 | 2024-12-10 | IT | IT | Payment Ais 1/11/2024 - 30/11/2024 | IT | Mong | Waiting for HQ to review. | WIP | 2024-12-11 | 1 Days |  | 12/12: Waiting Payment
33 | 2024-12-11 | PUR | NUII | Install meeting programs for the purchasing department. | EQ | Mong | Install tencent meeting program for User | Done | 2024-12-11
31 | 2024-12-10 | DCC | Doris | Request to register for an email account. | EMAIL | Mong | Create a memo document and request approval according to the procedure. | Done | 2024-12-11 | 1 Days | 2024-12-11
32 | 2024-12-10 | FIN | May | Computer Jack RJ45 internet lost connection | EQ | Than | Repair Boot jack RJ45 | Done | 2024-12-10 | 0 Days | 2024-12-10
33 | 2024-12-10 | GMO | Andy | Request lock print black and white in printer office | EQ | Than | Fixed in web console print management | Done | 2024-12-10 |  | 2024-12-10
34 | 2024-12-11 | ADM | Jaitip | Excel file format full | IT | Than | fixed format excel | Done | 2024-12-11 |  | 2024-12-11
35 | 2024-12-11 | QC | Nitradi | Outlook Email has offline mode display | Email | Than | Fixed Network metrics in windows limit internet | Done | 2024-12-11 |  | 2024-12-11
36 | 2024-12-11 | DCC | Jeai | Install an office printer on your computer. | EQ | Mong | Register and install Driver for User | Done | 2024-12-11 |  | 2024-12-11
37 | 2024-12-10 | ADM | MEAW | omputer is running slower than usual. | EQ | Mong | Uninstall unused programs and update drivers. | Done | 2024-12-11 |  | 2024-12-11
38 | 2024-12-10 | DCC | Chia | Install Microsoft and Activate so can use it. | EQ | Mong | Install Microsoft and Activate so can use it. | Done | 2024-12-11 |  | 2024-12-11
39 | 2024-12-13 | ADM | Jaitip | Request Excel formula format conditional formatting | IT | Than | Edit Excel formulas | Done | 2024-12-13 |  | 2024-12-13
40 | 2024-12-13 | ADM | Jefferry | Laptop cannot print. | IT | Mong | Set up a printer on laptop | Done | 2024-12-13 |  | 2024-12-13

## 工作表1 (hidden)
Issue_Date | Department | Request_User | Issue_Details | Issue_Type | DRI | Solution | Status | Last_Update_Date | Finished_Date | Remark
2024-11-07 | 8 |  | Request to purchase 4 tablets. | 6 | 2 | Procurement according to the process. | WIP | 2024-11-20 |  | 11/12 : Wait fin Payment 2024/11/20
2024-11-12 | 9 |  | Request to purchase printer. | 6 | 2 | Procurement according to the process. | WIP | 2024-11-20 |  | 11/12 : Find a quote 11/14 : Wait MR.Ashton 11/15: Wait IT HQ 11/19 : Waiting for GM approval. 11/20：總經理助理因個人情緒拒收
2024-11-18 | 12 |  | Request to purchase PC. | 6 | 2 | Procurement according to the process. | WIP | 2024-11-20 |  | 11/18: Wait IT HQ 11/19 : Waiting for GM approval. 11/20：總經理助理因個人情緒拒收
2024-11-12 | 11 | 2 | Pay AIS internet service fee for Oct. | 6 | 2 | Pay AIS internet service fees for October | WIP | 2024-11-20 |  | 11/12 : Wait fin Payment 2024/11/20
2024-11-14 | 5 |  | Request Email Account for new employee | 5 | 3 | Email Account register process | WIP | 2024-11-19 |  | 11/14 : Email sending a MEMO to request an Email account for the Purchase Department to HQ
帳號申請

## Member
Ashton | DCC
Mong | EQ
Than | IT
小汪 | Email
小繆 | Purchase
小袁 | ERP
小李

## Dept.
ADM
CMO | WIP
DCC | Done
EHS
FIN
GMO
IT
MFG
NPI
PMC
PUR
QC